## Jan-Dec, 2024
2024
| Date | Day | EVENTS NAME (event, national holiday/non-working day, deadlines) | Type of event | Location (if relevant) | Country (if relevat) | Pillar (if relevant) | Organiser | Additional information
JANUARY | 1 | Pon | AL, BA, BE, EL, HR, IT, ME, MK, RS, SI, SM | national holiday
| 2 | Tue | AL, BA, BE, ME, RS, SI | national holiday
Weekend
| 3 | Wed | [7 empty] | Holiday/non-working day
| 4 | Thu
| 5 | Fri
| 6 | Sat
| 7 | Sun
| 8 | Mon | BA, ME, MK, RS | national holiday
|  |  | Sending of 1st draft Governance Architecture paper to NCs | mailing |  |  |  | FACILITY POINT MACROREGIONAL | on behal of Presidency
| 9 | Tue
| 10 | Wed | Sending of written remarks on 1st draft Youth Council concept paper by Task Force members | deadline |  |  |  | FACILITY POINT MACROREGIONAL
| 11 | Thu
| 12 | Fri
| 13 | Sat
| 14 | Sun
| 15 | Mon | Mailing of 2nd draft Youth Council concept paper by FP LP to Task Force members | mailing |  |  |  | FACILITY POINT MACROREGIONAL
| 16 | Tue
| 17 | Wed
| 18 | Thu
| 19 | Fri
| 20 | Sat
| 21 | Sun
| 22 | Mon | Updated AP chapters on the Pillars for horizontal/X.cutting & indicators | deadline |  |  |  | FACILITY POINT MACROREGIONAL | to be sent from Pillar Coordinators to HR Presidency, EC and FP LP
|  |  | Sending of final remarks or silent agreement on 2nd Draft Youth Council concept paper by Task Force members | deadline |  |  |  | FACILITY POINT MACROREGIONAL | to be sent by TF members
| 23 | Tue
| 24 | Wed | Joint Steering Committe meeting | meeting | Trieste | Italy |  | 3 governance support projects
|  |  | GB WP opening on EUSAIR Youth Council concept paper | mailing |  |  |  | FACILITY POINT MACROREGIONAL | deadline 15/02, silent rule applies
| 25 | Thu | Joint Steering Committe meeting | meeting | Trieste | Italy |  | 3 governance support projects
| 26 | Fri | Deadline for sending revisions on the Governanc Architecture 1st Draft from NCs | deadline |  |  |  |  | to be sent as reply to all by National Coordinators
| 27 | Sat
| 28 | Sun
| 29 | Mon
| 30 | Tue
| 31 | Wed | [6 empty] | FP LP
FEBRUARY | 1 | Thu | Planed sending of 2nd Draft of the Governance Architecture paper | mailing |  |  |  | FACILITY POINT MACROREGIONAL | on behal of Presidency
|  |  | Sending of GB materials for approval | mailing |  |  |  | FACILITY POINT MACROREGIONAL
|  |  | EUSALP Slovenian Presidency Kick-Off | event | Postojna | Slovenia |  | OTHERS
| 2 | Fri
| 3 | Sat
| 4 | Sun
| 5 | Mon | SM | national holiday |  | San Marino
| 6 | Tue
| 7 | Wed
| 8 | Thu | SI | national holiday |  | Slovenia
| 9 | Fri
| 10 | Sat
| 11 | Sun
| 12 | Mon | Sending of remarks on 2nd Draft of the Governance Architecture paper from NCs | deadline |  |  |  |  | as reply to all to be sent by National Coordinators
| 13 | Tue
| 14 | Wed
| 15 | Thu | RS | national holiday |  | Serbia
|  |  | GB WP on EUSAIR Youth Council concept paper - closing | deadline |  |  |  | FACILITY POINT MACROREGIONAL | silent rule applies
| 16 | Fri | RS | national holiday |  | Serbia
| 17 | Sat
| 18 | Sun
| 19 | Mon | MC IPA ADRION | meeting |  |  |  | IPA ADRION
| 20 | Tue | MC IPA ADRION | meeting |  |  |  | IPA ADRION
| 21 | Wed | Kick off conference of 3 governance support projects | event | Zagreb | Croatia |  | 3 governance support projects | HR Presidency
|  |  | 22nd EUSAIR Governing Board | meeting | Zagreb | Croatia |  | FACILITY POINT MACROREGIONAL | HR Presidency
| 22 | Thu | 22nd EUSAIR Governing Board | meeting | Zagreb | Croatia |  | FACILITY POINT MACROREGIONAL | HR Presidency
| 23 | Fri
| 24 | Sat
| 25 | Sun
| 26 | Mon
| 27 | Tue
| 28 | Wed
| 29 | Thu
| 1 | Fri | BA | national holiday |  | Bosnia and Hercegovina
| 2 | Sat
MARCH
| 3 | Sun
| 4 | Mon
| 5 | Tue
| 6 | Wed | Sending of any new comments on Youth Council Concept paper | deadline |  |  |  | FACILITY POINT MACROREGIONAL | 22nd GB follow up
| 7 | Thu
| 8 | Fri | Meeting Pillar 2 - energy regarding gas issues - finalisation of the Action Plan | meeting | online |  | Pillar 2 | EUROPEAN COMMISSION
| 9 | Sat
| 10 | Sun
| 11 | Mon | TF Meeting Pillar 3 - indicators - finalisation of the Action Plan | meeting | online |  | Pillar 3 | EUROPEAN COMMISSION
| 12 | Tue | Deadline for sending any new comments on Governance Architecture Paper | deadline |  |  |  | FACILITY POINT MACROREGIONAL | 22nd GB follow up
| 13 | Wed
| 14 | Thu | AL | national holiday |  | Albania
|  |  | Biodiversity and Marine Protection in EUSAIR: A Contribution to EU Biodiversity Strategy 2030 | event | Brussels | Belgium | Pillar 3 | FACILITY POINT MACROREGIONAL
| 15 | Fri
| 16 | Sat
| 17 | Sun
| 18 | Mon | EL | national holiday |  | Greece
|  |  | TF Meeting Pillar 3 - indicators - finalisation of the Action Plan | meeting | online |  |  | FACILITY POINT MACROREGIONAL | 14.00 CET
|  |  | Sending of 1st draft of Pillar 3 indicators by Pillar Coordinators | deadline
| 19 | Tue
| 20 | Wed
| 21 | Thu
| 22 | Fri | AL | national holiday |  | Albania
|  |  | TF Meeting Pillar 3 - indicators - finalisation of the Action Plan | meeting | online
|  |  | Extraordinary TSG 3 meeting on indicators | meeting | online
| 23 | Sat
| 24 | Sun
| 25 | Mon | EL, SM | national holiday
| 26 | Tue | Youth Consultation Task Force meeting | meeting | online |  |  | FACILITY POINT MACROREGIONAL
| 27 | Wed
| 28 | Thu |  | national holiday |  | Belgium
| 29 | Fri | IT, BE, BA | national holiday |  | Belgium
| 30 | Sat
| 31 | Sun
APRIL | 1 | Mon | AL, BA, BE, HR, IT, SI, SM | national holiday
| 2 | Tue
| 3 | Wed
| 4 | Thu
| 5 | Fri
| 6 | Sat
| 7 | Sun
| 8 | Mon | 20th TSG 3 meeting | meeting | Zagreb | Croatia | Pillar 3 | FACILITY POINT MACROREGIONAL | Starts at 14.00
| 9 | Tue | 20th TSG 3 meeting | meeting | Zagreb | Croatia | Pillar 3 | FACILITY POINT MACROREGIONAL | ends at 12.00
| 10 | Wed | AL, BA, MK | national holiday
| 11 | Thu | BA | national holiday
| 12 | Fri | BA | national holiday
| 13 | Sat
| 14 | Sun
| 15 | Mon
| 16 | Tue
| 17 | Wed
| 18 | Thu
| 19 | Fri
| 20 | Sat
| 21 | Sun
| 22 | Mon
| 23 | Tue | Conference on the implementation of the 2030 EU Biodiversity Strategy in the Adriatic Sea through joint solutions for nature and fisheries | event | Zadar | Croatia | Pillar 1 | FACILITY POINT MACROREGIONAL | * working title
|  |  | 19th TSG 2 - Energy | meeting | online |  | Pillar 2 | FACILITY POINT MACROREGIONAL | 10.00-13.00
|  |  | 23rd TSG 4 meeting | meeting | online |  | Pillar 4 | FACILITY POINT MACROREGIONAL | 10:00-12:15
| 24 | Wed
| 25 | Thu | Conference on transport connectivity in the AIR: Western Balkans - Eastern Mediterranean Corridor | event | Zagreb | Croatia | Pillar 2 | FACILITY POINT MACROREGIONAL
|  |  | IT | national holiday |  | Italy
| 26 | Fri | TSG 2 - Transport meeting | meeting | online |  | Pillar 2 | FACILITY POINT MACROREGIONAL | 10:30-13:30
| 27 | Sat
| 28 | Sun
| 29 | Mon
| 30 | Tue
MAY | 1 | Wed | AL, BA, BE, EL, HR, IT, ME, MK, RS, SI, SM | national holiday
| 2 | Thu | BA,ME, RS,SI | national holiday
| 3 | Fri | BA, EL, ME, MK, RS | national holiday
| 4 | Sat
| 5 | Sun
| 6 | Mon | AL, BA, EL, ME, MK, RS | national holiday
| 7 | Tue | EL | national holiday
| 8 | Wed
| 9 | Thu | BE, BE, RS | national holiday
| 10 | Fri |  |  |  | Belgium
| 11 | Sat
| 12 | Sun
| 13 | Mon
| 14 | Tue | 9th EUSAIR Forum - side events | event | Šibenik | Croatia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 15 | Wed | 9th EUSAIR Forum | event | Šibenik | Croatia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 16 | Thu | 9th EUSAIR Forum | event | Šibenik | Croatia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 17 | Fri | 9th EUSAIR Forum - side events | event | Šibenik | Croatia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 18 | Sat
| 19 | Sun
| 20 | Mon | BE | national holiday |  | Belgium
| 21 | Tue | ME | national holiday |  | Montenegro
| 22 | Wed | ME | national holiday |  | Montenegro
| 23 | Thu
| 24 | Fri | MK | national holiday |  | North Macedonia
| 25 | Sat
| 26 | Sun
| 27 | Mon
| 28 | Tue
| 29 | Wed
| 30 | Thu | HR, SM | national holiday
| 31 | Fri
JUNE | 1 | Sat
| 2 | Sun
| 3 | Mon
| 4 | Tue
| 5 | Wed
| 6 | Thu
| 7 | Fri
| 8 | Sat
| 9 | Sun
| 10 | Mon
| 11 | Tue
| 12 | Wed | 5th EU Macro-Regional and Sea Basin Strategies Days | event | Brussels | Belgium |  | EUROPEAN COMMISSION | Venue: The Egg
| 13 | Thu | 5th EU Macro-Regional and Sea Basin Strategies Days | event | Brussels | Belgium |  | EUROPEAN COMMISSION
| 14 | Fri | 5th EU Macro-Regional and Sea Basin Strategies Days | event | Brussels | Belgium |  | EUROPEAN COMMISSION
| 15 | Sat
| 16 | Sun
| 17 | Mon | AL, BA | national holiday
| 18 | Tue | BA | national holiday
| 19 | Wed | BA | national holiday
| 20 | Thu | 13th Annual Forum of the EU Strategy for the Danube Region | event | Vienna | Other |  | EUSDR
| 21 | Fri | MK | national holiday |  |  |  | EUSDR
|  |  | 13th Annual Forum of the EU Strategy for the Danube Region | event | Vienna | Other
| 22 | Sat
| 23 | Sun
| 24 | Mon | EL | national holiday |  | Greece
| 25 | Tue | SI | national holiday |  | Slovenia
| 26 | Wed
| 27 | Thu
| 28 | Fri | RS | national holiday
| 29 | Sat
| 30 | Sun
JULY | 1 | Mon
| 2 | Tue
| 3 | Wed
| 4 | Thu
| 5 | Fri
| 6 | Sat
| 7 | Sun
| 8 | Mon
| 9 | Tue
| 10 | Wed
| 11 | Thu
| 12 | Fri | BA | national holiday
| 13 | Sat
| 14 | Sun
| 15 | Mon | ME | national holiday |  | Montenegro
| 16 | Tue
| 17 | Wed
JULY | 18 | Thu
| 19 | Fri
| 20 | Sat
| 21 | Sun
| 22 | Mon
| 23 | Tue
| 24 | Wed
| 25 | Thu
| 26 | Fri
| 27 | Sat
| 28 | Sun
| 29 | Mon
| 30 | Tue
| 31 | Wed
AUGUST | 1 | Thu
| 2 | Fri | BA, MK | national holiday |  | North Macedonia
| 3 | Sat
| 4 | Sun
| 5 | Mon | HR | national holiday |  | Croatia
| 6 | Tue
| 7 | Wed
| 8 | Thu
| 9 | Fri
| 10 | Sat
| 11 | Sun
| 12 | Mon
| 13 | Tue
| 14 | Wed
AUGUST | 15 | Thu | BA, BE, HR, EL, IT, SI, SM | national holiday
| 16 | Fri
| 17 | Sat
| 18 | Sun
| 19 | Mon
| 20 | Tue
| 21 | Wed
| 22 | Thu
| 23 | Fri
| 24 | Sat
| 25 | Sun
| 26 | Mon
| 27 | Tue
| 28 | Wed | BA, MK | national holiday
| 29 | Thu
| 30 | Fri
| 31 | Sat
SEPTEMBER | 1 | Sun
| 2 | Mon
| 3 | Tue | SM | national holiday |  | San Marino
| 4 | Wed
| 5 | Thu | AL | national holiday |  | Albania
| 6 | Fri
| 7 | Sat
| 8 | Sun
| 9 | Mon | MK | national holiday |  | North Macedonia
| 10 | Tue
| 11 | Wed
| 12 | Thu
| 13 | Fri
| 14 | Sat
| 15 | Sun
SEPTEMBER | 16 | Mon | Week of mediterranean cost and macroregional strategies | event | Izola, Portorož | Slovenia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 17 | Tue | Week of mediterranean cost and macroregional strategies | event | Izola, Portorož | Slovenia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 18 | Wed | Week of mediterranean cost and macroregional strategies | event | Izola, Portorož | Slovenia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 19 | Thu | Week of mediterranean cost and macroregional strategies | event | Izola, Portorož | Slovenia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 20 | Fri | Week of mediterranean cost and macroregional strategies | event | Izola, Portorož | Slovenia | Cross Pillar | FACILITY POINT MACROREGIONAL
| 21 | Sat
| 22 | Sun
| 23 | Mon
| 24 | Tue
| 25 | Wed
| 26 | Thu
| 27 | Fri
| 28 | Sat
| 29 | Sun
| 30 | Mon
OCTOBER | 1 | Tue | SM | national holiday |  | San Marino
| 2 | Wed
| 3 | Thu
| 4 | Fri
| 5 | Sat
| 6 | Sun
| 7 | Mon
| 8 | Tue
| 9 | Wed
| 10 | Thu
| 11 | Fri | MK | national holiday |  | North Macedonia
| 12 | Sat
| 13 | Sun
| 14 | Mon
| 15 | Tue
OCTOBER | 16 | Wed
| 17 | Thu
| 18 | Fri
| 19 | Sat
| 20 | Sun
| 21 | Mon | RS | national holiday
| 22 | Tue
| 23 | Wed | MK | national holiday |  | North Macedonia
| 24 | Thu
| 25 | Fri
| 26 | Sat
| 27 | Sun
| 28 | Mon | EL | national holiday |  | Greece
| 29 | Tue
| 30 | Wed
| 31 | Thu | SI | national holiday |  | Slovenia
NOVEMBER | 1 | Fri | BA, BE, HR, IT, SI, SM | national holiday
| 2 | Sat
| 3 | Sun
| 4 | Mon
| 5 | Tue
| 6 | Wed
| 7 | Thu
| 8 | Fri | BA | national holiday
| 9 | Sat
| 10 | Sun
| 11 | Mon | BE, RS | national holiday |  | Serbia
| 12 | Tue
| 13 | Wed | ME | national holiday |  | Montenegro
| 14 | Thu |  |  |  | Montenegro
| 15 | Fri | BE | national holiday
NOVEMBER
| 16 | Sat
| 17 | Sun
| 18 | Mon | HR | national holiday |  | Croatia
| 19 | Tue
| 20 | Wed
| 21 | Thu | BA | national holiday
| 22 | Fri
| 23 | Sat
| 24 | Sun
| 25 | Mon | BA | national holiday |  | Bosnia and Hercegovina
| 26 | Tue
| 27 | Wed
| 28 | Thu | AL | national holiday |  | Albania
| 29 | Fri | AL | national holiday |  | Albania
| 30 | Sat
DECEMBER | 1 | Sun
| 2 | Mon
| 3 | Tue
| 4 | Wed
| 5 | Thu
| 6 | Fri | BE | national holiday
| 7 | Sat
| 8 | Sun
| 9 | Mon | AL, MK | national holiday
| 10 | Tue
| 11 | Wed
| 12 | Thu
| 13 | Fri
| 14 | Sat
| 15 | Sun
| 16 | Mon
| 17 | Tue
| 18 | Wed
| 19 | Thu
| 20 | Fri
| 21 | Sat
| 22 | Sun
| 23 | Mon |  |  |  | Belgium
| 24 | Tue | EL, HR, SM | national holiday
| 25 | Wed | AL, BA, BE, EL, HR, IT, ME, MK, RS, SI, SM | national holiday
| 26 | Thu | BE, HR, EL, IT, ME, SI, SM | national holiday
| 27 | Fri |  |  |  | Belgium
| 28 | Sat
| 29 | Sun
| 30 | Mon |  |  |  | Belgium
| 31 | Tue | BE, EL, HR, IT, SM |  |  | Belgium

## Drop-down (2) (hidden)
Legend
| PILLARS | ORGANISER | COUNTRIES
1 | Pillar 1 | FACILITY POINT MACROREGIONAL | Albania
2 | Pillar 2 | FACILITY POINT NATIONAL | Bosnia and Hercegovina
3 | Pillar 3 | 3 governance support projects | Croatia
4 | Pillar 4 | StEP | Greece
5 | Pillar 5 | Strategic Implementation | Italy
6 | Cross Pillar | EUROPEAN COMMISSION | Montenegro
|  | Adriatic Ionian Initiative | North Macedonia
|  | EUSDR | San Marino
|  | INTERACT | Serbia
|  | IPA ADRION | Slovenia
|  | OTHERS | Belgium
Other
Type of event
event
meeting
national holiday
mailing
deadline

## Drop-down (hidden)
Legend
| PILLARS | ORGANISER | COUNTRIES
1 | Pillar 1 | EUSAIR FACILITY POINT MACROREGIONAL | Albania
2 | Pillar 2 | EUSAIR FACILITY POINT NATIONAL | Bosnia and Hercegovina
3 | Pillar 3 | EUROPEAN COMMISSION | Croatia
4 | Pillar 4 | Adriatic Ionian Initiative | Greece
5 | Pillar 5 | AI- NURECC | Italy
6 | Cross Pillar | EUSDR | Montenegro
|  | INTERACT | North Macedonia
|  | IPA ADRION | San Marino
|  | OTHERS | Serbia
Slovenia
Belgium
Other
Type of event
event
meeting
national holiday
mailing
deadline