{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["WORKPLAN 2025","WORKLPAN 2024","Drop-downs","Drop-down"],"not_rendered":{"charts":0,"images":3,"macros":1,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"WORKPLAN 2025","index":0,"n_rows":114,"n_cols":17,"rows_kept":114,"cut":false,"hidden":false,"merged":[[3,9,4,9],[3,10,4,10],[3,12,3,13],[3,11,4,11],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,4,4,4],[3,5,4,5],[3,3,4,3]]}
[]
["ANNUAL EUSAIR WORKPLAN FOR 2025"]
["Prepared by EGP in cooperation with Pillar Coordinators and Presidency including all EUSAIR  events and main activities/processes regardless of funding source"]
["Type of activity","Title of event\n\nTitle of activity (and phase if relevant)","Term\nDuration\n(quarter of the year)","Date, if relevant (DAY/MONTH/YEAR)","Level - macro-regional, national, regional/local","Location country, if relevant\n\nOnline","Location town, if relevant\n\nHybrid","Target groups\n\nInvolved\n","Pillar related ","Main organiser \n(more details to be provided in column N)","Other important information","Communication coverage needs foreseen","Only for events/activities- supported by EGP",null,null,null,"- selection from drop down"]
[null,null,null,null,null,null,null,null,null,null,null,null,"Application Form\nNo. of Work Package \nNo. of activity","PPs involved"]
["Meeting","EUSAIR Youth Council 2nd Membership Meeting ","Q1","13/01/2025","macroregional","Online",null,"Youth Council","Cross pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3","LP"]
["Meeting","Action Lab 1 - Embedding in practice: triggers,\nobstacles and best practices\nto gauge the programmes’\nimplementation to the\nmacro-regional strategy","Q1","14/01/2025","macroregional","Online",null,"TSG and PCs, Stakeholders, MAs/Funds coordination authorities","Cross pillar","StEP",null,null,"WP4, Act. 4.4","LP StEP"]
["Meeting","Youth Consultation Task Force 10th meeting","Q1","23/01/2025","macroregional","ONLINE",null,"Task Force","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.1","LP"]
["Meeting","8th Meeting of the EGP Projects’ Lead Partners ","Q1","30-31/01/2025","macroregional","Italy","Trieste","EGP",null,"EGP",null,null,"WP2,Act.2.3","all LPs"]
["Event","Capacity building workshop for TSG 4","Q1","03/02/2025","macroregional","ONLINE",null,"TSG and PCs","Pillar 4","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, PP SP4EUSAIR"]
["Event","Capacity building workshop for TSG 5","Q1","06/02/2025","macroregional","ONLINE",null,"TSG and PCs","Pillar 5","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, PP SP4EUSAIR"]
["Meeting","Preparatory meeting for capacity building","Q1","07/02/2024","national","Slovenia","Izola",null,"Cross Pillar","Facility Point  - national",null,null,"WP3,Act.3.2","PP10-OI"]
["Event","Unlocking Opportunities for Post-2027 Europe: EUSAIR, Interreg, and Cohesion Policy in Joint Action","Q1","07/02/2025","macroregional","Greece","Thessaloniki","all","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Meeting","EUSAIR 24th Governing Board Meeting","Q1","13/02/2025","macroregional","Greece","Patras","Governing Board","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.1","LP, PP5-EYSSAE"]
["Meeting","EUSAIR National and Pillar Coordinator technical meetings","Q1","12/02/2025","macroregional","Greece","Patras","Governing Board","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.1","LP, PP5-EYSSAE"]
["Event","Capacity building workshop for TSG 1","Q1","21/02/2025","macroregional","ONLINE",null,"TSG and PCs","Pillar 1","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, PP SP4EUSAIR"]
["Meeting","StEP, WP5, Presentation of the first deliverables ","Q1","21/2/2025","macroregional","ONLINE","ESP","Stakeholders","Cross Pillar","StEP"," "," ","WP5, Act. 5.1","StEP - PP2"]
["Meeting","22nd Meeting of EUSAIR TSG2 on Transport","Q1","25/02/2025","macroregional","Online",null,"TSG and PCs","Pillar 2 - Transport","Facility Point - macroregional",null,null,"WP1, Act. 1.2","PP6 RAFVG"]
["Activity","Pillar Annual Progress Reports 2024","Q1","28/02/2025","macroregional",null,null,"TSG and PCs","Cross Pillar","Facility Point - macroregional",null,null,"WP1, Act.1.2","all"]
["Event","Promoting policies and practices for skills in the macroregion","Q1","4-5/03/2025","macroregional","Greece","Athens & hybrid ","all","Pillar 5","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Meeting","National coordination on MRSs implementation","Q1","05/03/2025","national","Slovenia","Brdo pri Kranju",null,"Cross Pillar","OTHERS (please indicate who in column K)","National Coordination",null,"WP2,Act.2.4","LP, PP10-OI"]
["Meeting","EUSAIR Youth Council 3rd Membership Meeting ","Q1","06/03/2025 ","macroregional","Online",null,"Youth Council","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3","LP"]
["Meeting","Meeting of national WG for EUSAIR","Q1","11/03/2025 ","national","Montenegro","Podgorica","Working group","Cross Pillar","Facility Point  - national"," ","no","WP1,Act.1.2","PP7-MEA"]
["Event","Prospects for Energy Network Development, Hydrogen Market, Offshore Potential: Challenges and Solutions for the Adriatic-Ionian Macro-Region","Q1","12/03/2025","cross-MRS","Greece","Athens & hybrid ","all","Pillar 2 - Energy","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Event","Capacity building workshop for TSG 3","Q1","13/03/2025","macroregional","Other",null,"TSG and PCs","Pillar 3","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, PP SP4EUSAIR"]
["Event","Promotion of TSG 3 EUSAIR achievements and collaboration with UNEP/MAP at the 50th Anniversary of the Barcelona Convention ","Q1","26/03/2025","macroregional","Belgium","Brussels","TSG and PCs","Pillar 3","EUROPEAN COMMISSION ",null,null,"WP1,Act.1.2"]
["Event","Interreg GO 2025","Q1","27-28/03/2025","cross-MRS","Italy and Slovenia","Gorizia (IT) and Nova Gorica (SI)","all","Cross Pillar","EUROPEAN COMMISSION ","The conference is organized in partnership with the Interreg Italy-Slovenia programme, the EGTC GO!, the Friuli-Venezia-Giulia region in Italy and the Ministry for Cohesion and Regional Development in Slovenia, as well as with Interact."]
["Activity","Capacity building programme","Q1","March","macroregional",null,null,"all","Cross Pillar","Facility Point - macroregional",null,null,"WP3, Act.3.2","PP10-OI, PP7-MEA"]
["Activity","Newcomers kit","Q1","March","macroregional",null,null,"all","Cross Pillar","Facility Point - macroregional",null,null,"WP3, Act.3.2","PP10-OI, PP7-MEA"]
["Activity","Post-2027 Cohesion Policy Report","Q1","March","macroregional",null,null,"all","Cross Pillar","Facility Point - macroregional",null,null,"WP3, Act.3.1","LP"]
["Activity","Common visual identity development","Q1","March","macroregional",null,null,"all","Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.1","LP"]
["Activity","EUSAIR Youth Council (membership prolongation/new members)","Q3","March","macroregional",null,null,"Youth Council","Cross Pillar","Facility Point - macroregional",null,null,"WP1, Act.1.3","LP"]
["Activity","Starting the work the newly hired Project Manager","Q1","End of March 2025","national","Albania","Tirana"," "," ","StEP"," "," ","WP3","P3-SASPAC"]
["Activity","Starting the work the newly hired Financial Manager","Q1","End of March 2025","national","Albania","Tirana"," "," ","StEP"," "," ","WP3","P3-SASPAC"]
["Activity","Starting the work the newly hired Communication Officer","Q1","End of March 2025","national","Albania","Tirana"," "," ","StEP"," "," ","WP3","P3-SASPAC"]
["Meeting","Action Lab 2 - Capitalization of the programmes’\nimplementation to the\nmacro-regional strategy","Q2","02/04/2025","cross-MRS","ONLINE","ESP","TSG and PCs, Stakeholders, MAs/Funds coordination authorities","Cross Pillar","StEP",null,null,"WP4, Act. 4.4","LP StEP"]
["Event","2nd TSG5 Meeting","Q2","3-4/04/2025","macroregional","Croatia","Zadar","TSG and PCs","Pillar 5","Facility Point - macroregional",null,null,"WP1,Act.1.2","PP4-MINTS"]
["Meeting","22th TSG Pillar 3 Meeting ","Q2","07/04/2025","macroregional","Greece","Corfu","TSG and PCs","Pillar 3","Facility Point - macroregional",null,null,"WP1,Act.1.2","PP5-EYSSAE"]
["Meeting","LIFE-IP AdaptInGR Workshop ''Accelerating climate change adaptation in the Adriatic-Ionian Region''","Q2","8-9/04/2025","macroregional","Greece","Corfu","all","Pillar 3","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Meeting","21st TSG 1 Meeting","Q1","09/04/2025","macroregional","Montenegro","Podgorica","TSG and PCs","Pillar 1","Facility Point - macroregional",null,null,"WP1,Act.1.2","PP7-MEA"]
["Meeting","25th TSG 4 Meeting","Q1","11/04/2025","macroregional",null,"online","TSG and PCs","Pillar 4","Facility Point - macroregional",null,null,"WP1,Act.1.2","PP5-EYSSAE, PP4-MINTS"]
["Meeting","21st Meeting of EUSAIR TSG2 on Energy ","Q2","15/04/2025","macroregional","Serbia","Belgrade","TSG and PCs","Pillar 2 - Energy","Facility Point - macroregional",null,null,"WP1, Act. 1.2","PP6 RAFVG"]
["Event","Capacity building workshop for TSG 2 on Transport","Q1","April-June","macroregional","Other","TBD","TSG and PCs","Pillar 2 - Transport","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, PP SP4EUSAIR"]
["Event","Capacity building workshop for TSG 2 on Energy","Q1","30/04/2025","macroregional","Other","online","TSG and PCs","Pillar 2 - Energy","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, PP SP4EUSAIR"]
["Activity","EUSAIR Achivements (Strategy and Pillars) in 10 years (publication) and stories from 10 countries","Q2","April, May","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.1","LP"]
["Meeting","5th Informal meeting of EU MRS Supporting Units","Q2","05/05/2025","macroregional","Greece","Crete",null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.4","LP"]
["Meeting","EUSAIR Youth Council 4th Membership Meeting ","Q2","06/05/2025","macroregional","Greece","Crete","Youth Council","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3","LP"]
["Event","10th EUSAIR Forum","Q2","6-7/05/2024","cross-MRS","Greece","Crete","all","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Meeting","Youth Consultation Task Force 11th meeting","Q2","13/05/2025","macroregional","ONLINE",null,"Task Force","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.1","LP"]
["Event","Conference: \"Climate Resilience Policies for Coastal Cultural Heritage in the Adriatic-Ionian Region\"","Q2","17-18/05/2025","macroregional","Greece","Kastoria","TSG and PCs","Cross Pillar","EUSAIR Presidency and AII"]
["Meeting","Capacity building meeting of EGP (in cooperation with Interact)","Q2","20-21/05/2025","macroregional","Italy","Ancona","EGP","Cross Pillar","EGP",null,null,"WP3, Act.3.2","PP10-OI, PP7-MEA"]
["Event","YOUth Shape EU: Bridging Borders, Building Belonging","Q2","28/05/2025","macroregional","Italy","Ancona","all","Cross Pillar","IVY programme, IPA ADRION NCP Italy and GEAR UP! project"]
["Meeting","Action Lab 3 – Evaluation of ETC programmes’ contribution to EUSAIR","Q2","10/06/2025","cross-MRS","ONLINE","ESP","TSG and PCs, Stakeholders, MAs/Funds coordination authorities","Cross Pillar","StEP",null,null,"WP4, Act. 4.4","LP StEP"]
["Meeting","Mainstream – RIS 3 MAs Network on-line event \n","Q2","June/July","cross-MRS","ONLINE","ESP","TSG and PCs, Stakeholders, MAs/Funds coordination authorities","Cross Pillar","StEP",null,null,"WP4, Act. 4.4","LP StEP"]
["Activity","6 Thematic steering group working report on key strategic ideas","Q2","April-June","macroregional",null,null,"TSG and PCs","Cross Pillar","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, SP4EUSAIR"]
["Activity","Knowledge based report on established key strategic ideas","Q2","April-June","macroregional",null,null,"TSG and PCs","Cross Pillar","Strategic Implementation",null,null,"WP1, Act. 1.2","LP, SP4EUSAIR"]
["Event","\"Enhancing Road and Rail Connectivity in the Adriatic-Ionian Region. Addressing Cross-Border Challenges Through Institutional Dialogue and Chambers of Commerce Insights\"","Q2","18-19/06/2025","macroregional","Slovenia","Portorož","all","Cross Pillar","OTHERS (please indicate who in column K)","AIC Forum"]
["Meeting","EUSAIR Youth Council 5th Membership Meeting ","Q3","24/06/2025","macroregional","ONLINE",null,"Youth Council","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3","LP"]
["Event","25th Anniversary of the Adriatic-Ionian Initiative (AII)","Q2","27/06/2025","macroregional","Italy","Ancona","all","Cross Pillar","Adriatic Ionian Initiative"]
["Event","Workshop “Is the Future of Port Systems Still Green? – Balancing Decarbonisation, Competitiveness and Skills in the Adriatic-Ionian Macroregion”","Q2","27/06/2025","macroregional","ONLINE",null,"Stakeholders","Pillar 2","OTHERS (please indicate who in column K)","In the framework of the Workshop “Green and Smart Ports: Shaping the Future of Green Transition and Skills Development in the Adriatic-Ionian Region” which will be held on 16 October 2025 in Trieste, it is foreseen a preparatory activity for the engagement of all stakeholders of the area involved (Port Authorities, Terminal Operators, Universities and Training institutions). The activity consists in two online Workshops:\nIn the framework of the Workshop “Green and Smart Ports: Shaping the Future of Green Transition and Skills Development in the Adriatic-Ionian Region” which will be held on 16 October 2025 in Trieste, it is foreseen a preparatory activity for the engagement of all stakeholders of the area involved (Port Authorities, Terminal operators, Universities and Training institutions). The activity consists in two online Workshops:\n1)\tWorkshop “Is the Future of Port Systems Still Green? – Balancing Decarbonisation, Competitiveness and Skills in the Adriatic-Ionian Macroregion” for Port Authorities and Terminal Operators (27 June 2025)\n2)\tWorkshop (title tbd) for Universities and Training institutions (September 2025, tbd)\n\nThe preparatory activity comprehends also the circulation of dedicated questionnaires, whose results will be the base of the discussion of the two Workshops.","yes","WP1, Act. 1.2","PP6 RAFVG"]
["Meeting","3rd Project Steering Group Meeting","Q3","9-10/07/2025","macroregional","Bosnia and Hercegovina","Sarajevo",null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.3","all"]
["Event","Skillman Alliance Summit 2025","Q3","9-10/07/2025","macroregional","Italy","Ancona","all","Cross Pillar","OTHERS (please indicate who in column K)","EUSAIR Presidency, Skillman Network, Università Politecnica delle Marche"]
["Activity","Manual to define a set of criteria for IFs and rules for\nthe development of concept documents","Q3","July-September","macroregional",null,null,"TSG and PCs","Cross Pillar","Strategic Implementation",null,null,"WP1, Act. 1.3","LP, SP4EUSAIR"]
["Activity","Pipeline of selected implementation formats","Q3","July-September","macroregional",null,null,"Governing Board","Cross Pillar","Strategic Implementation",null,null,"WP1, Act. 1.4","LP, PP SP4EUSAIR"]
["Activity","Handbook for the preparation of project proposals for each strategic implementation format","Q3","July-September","macroregional",null,null,"TSG and PCs","Cross Pillar","Strategic Implementation",null,null,"WP2, Act. 2.1","LP SP4EUSAIR"]
["Activity","EUSAIR Stakeholder Database and its Qualitative Analysis","Q3","September","regional/local","Albania","Tirana"," "," ","StEP"," "," ","WP3, Act.1","P3-SASPAC"]
["Event","Workshop on educational needs for the implementation of the innovative technologies for the sustainability in the port sector (title tbd)","Q3","September (tbd)","macroregional","ONLINE",null,"Stakeholders","Cross Pillar","OTHERS (please indicate who in column K)","In the framework of the Workshop “Green and Smart Ports: Shaping the Future of Green Transition and Skills Development in the Adriatic-Ionian Region” which will be held on 16 October 2025 in Trieste, it is foreseen a preparatory activity for the engagement of all stakeholders of the area involved (Port Authorities, Terminal Operators, Universities and Training institutions). The activity consists in two online Workshops:\nIn the framework of the Workshop “Green and Smart Ports: Shaping the Future of Green Transition and Skills Development in the Adriatic-Ionian Region” which will be held on 16 October 2025 in Trieste, it is foreseen a preparatory activity for the engagement of all stakeholders of the area involved (Port Authorities, Terminal operators, Universities and Training institutions). The activity consists in two online Workshops:\n1)\tWorkshop “Is the Future of Port Systems Still Green? – Balancing Decarbonisation, Competitiveness and Skills in the Adriatic-Ionian Macroregion” for Port Authorities and Terminal Operators (27 June 2025)\n2)\tWorkshop (title tbd) for Universities and Training institutions (September 2025, tbd)\n\nThe preparatory activity comprehends also the circulation of dedicated questionnaires, whose results will be the base of the discussion of the two Workshops.","yes","WP1, Act. 1.2","PP6 RAFVG"]
["Meeting","9th Meeting of the EGP Projects’ Lead Partners ","Q4","2025-08-09","macroregional",null,null,"EGP",null,"EGP",null,null,"WP2,Act.2.3","all LPs"]
["Meeting","Coordination meeting between EUSAIR Pillar Coordinators and EUSAIR Facility Point \n","Q3","2025-11-09","macroregional","ONLINE",null,"Pillar Coordinators",null,"Facility Point - macroregional"]
["Event","REDETE25 - Researching Economic Development and Entrepreneurship in Transition Economies","Q3","11-12/09/2025","macroregional","Bosnia and Hercegovina","Banja Luka","all",null,"OTHERS (please indicate who in column K)","University of Banja Luka, Faculty of Economics and Università Politecnica delle Marche, Italy. The conference is part of EUSAIR Presidency of North Macedonia acitivities"]
["Event","Green Ports and the Skills of Tomorrow: Advancing Port Competences and Critical Success Factors for a Sustainable Maritime Transition","Q3","2025-12-09","macroregional","ONLINE",null,"TSG and PCs","Pillar 2","OTHERS (please indicate who in column K)"]
["Event","Mediterranean Coast and Macro-Regional Strategies Week 2025","Q3","15-18/09/2025","macroregional","Slovenia","Izola","all","Cross Pillar","Facility Point - macroregional",null,"yes","WP1, Act.1.2","LP, PP10-OI"]
["Event","EU Macro-Regional and Sea Basin Strategies Days 2025","Q3","24-25/09/2025","macroregional","Belgium","Brussels","all","Cross Pillar","EUROPEAN COMMISSION ",null,null,"WP2,Act.2.4"]
["Meeting","High level group and Four Trio’s meeting ","Q3","26/09/2025","macroregional","Belgium","Brussels","National Coordinators","Cross Pillar","EUROPEAN COMMISSION ",null,null,"WP2,Act.2.4","LP"]
["Event","Sustainable and Innovative Food Systems: The Mediterranean Diet as a Tool for Tourism and Local Development in EUSAIR Communities","Q3","29-30/09/2025","macroregional","Italy","Bari","all","Cross Pillar","EUSAIR Presidency"]
["Meeting","Meeting of national WG for EUSAIR","Q3","September","national","Montenegro","Podgorica","Working group","Cross Pillar","Facility Point  - national"," ","no","WP1,Act.1.2","PP7-MEA"]
["Event","Promoting EUSAIR in Montenegro – WS for stakeholders","Q3","September/October","national","Montenegro","tbd","Stakeholders","Cross Pillar","Facility Point  - national","Tentative event","yes - website, social media","WP3,Act.3.2","PP7-MEA"]
["Event","ICT strategies for integration of port intermodal nodes with hinterland in the Adriatic-Ionian Region: State ofthe art & future perspectives","Q3","2025-02-10","macroregional","Italy","Ravenna + online \n(Hybrid) ","all","Pillar 2 - Transport","OTHERS (please indicate who in column K)","The event is organized by the Emilia Romagna Region and the Port Authority of Ravenna, partners of Project Interreg ITA CRO 21-27 \"CROSSFREIGHT_” Crossborder ICT Strategies for Freight Rail and Port Logistics,Integration,Optimization and Security (LP ITL_ Istitute of Transport and Logistic Foundation). This project aligns with the EUSAIR Pillar 2 Flagship “Green/Smart Ports Hub” and aims to validate digital solutions (ICT) to enhance the management of operations and interconnections between intermodal and port nodes. The objective of the event is to analyze pilot actions to ensure the transferability of results at both regional and transregional levels within the AI area framework.",null,"WP1, Act. 1.2","PP6 RAFVG "]
["Activity","New joint plan for stakeholder engagement and involvement","Q3, Q4","October","regional/local","Albania","Tirana"," "," ","StEP"," "," ","WP3, Act.2","P3-SASPAC"]
["Activity","Contents and Format of Annual Reports Template","Q4","October","macroregional",null,null,"Governing Board","Cross Pillar","Facility Point - macroregional",null,null,"WP4,Act.4.1","PP5-EYSSAE"]
["Event","Pillar 4 related event within the European Heritage Days","Q4","7-8/10/2025","macroregional","North Macedonia","Bitola","TSG and PCs","Pillar 4","EUSAIR Presidency"]
["Event","European Week of Regions and Cities","Q4","13-15/10/2025","macroregional","Belgium","Brussels","all",null,"EUROPEAN COMMISSION "]
["Event","Workshop “Green and Smart Ports: Shaping the Future of Green Transition and Skills Development in the Adriatic-Ionian Region”","Q4","16/10/2025","macroregional","Italy","Trieste/ hybrid event","TSG and PCs, Stakeholders","Pillar 2, Pillar 5","OTHERS (please indicate who in column K)","The event, organized by CEI in collaboration with the Friuli Venezia Giulia Region, will be the follow-up  of the workshop on “Connecting the Adriatic-Ionian Region through Advanced Technology and Training for the Energy Transition in the Port Sector,” held in Trieste during November  2024. The workshop aims to deepen the dialogue on port decarbonization and skills development while extending its scope to encompass the entire Adriatic-Ionian macroregion. Starting from the outcomes of the previous event,  the workshop will focus on developing innovative strategies, fostering regional collaboration, and equipping the workforce with the green and digital competencies required for the energy transition. ",null,"WP1, Act. 1.2","PP6 RAFVG"]
["Meeting","23rd Meeting of EUSAIR TSG2 on Transport ","Q4","17/10/2025","macroregional","Italy","Trieste/ hybrid event","TSG and PCs","Pillar 2 - Transport","Facility Point - macroregional",null,null,"WP1, Act. 1.2","PP6 RAFVG"]
["Meeting","EUSAIR 25th Governing Board Meeting","Q4","21-22/10/2025 (TBC)","macroregional","North Macedonia","Skopje","Governing Board","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.1","LP, PP8-MEA"]
["Meeting","EUSAIR National and Pillar Coordinator technical meetings","Q4","tbc","macroregional",null,null,"Governing Board","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.1","LP, PP8-MEA"]
["Activity","Report on identified funding sources for each project proposal\n/implementation format","Q4","October-December","macroregional",null,null,"TSG and PCs","Cross Pillar","Strategic Implementation",null,null,"WP2, Act. 2.1","LP SP4EUSAIR"]
["Event","16th EUSBSR Annual Forum","Q4","28-30/10/2025","cross-MRS","Poland","Gdansk","all","Cross Pillar","OTHERS (please indicate who in column K)","PL EUSBSR PCY",null,"WP2,Act.2.4"]
["Event","14th EUSDR Annual Forum","Q4","05-06/11/2025","cross-MRS","Bosnia and Hercegovina","Sarajevo","all","Cross Pillar","OTHERS (please indicate who in column K)","BA NC, DSP",null,"WP2,Act.2.4"]
["Meeting","Joint Meeting of EUSDR and EUSAIR National Coordinators","Q4","06/11/2025","cross-MRS","Bosnia and Hercegovina","Sarajevo","National Coordinators","Cross Pillar","OTHERS (please indicate who in column K)","Facility Point - macroregional, BA NC, DSP"]
["Event","10th EUSALP Annual Forum","Q4","25-26/11/2025","cross-MRS","Austria","Innsbruck","all","Cross Pillar","OTHERS (please indicate who in column K)","AT and LI EUSALP PCY",null,"WP2,Act.2.4"]
["Meeting","22th TSG 1 Meeting","Q4","tbc","macroregional",null,null,"TSG and PCs","Pillar 1","Facility Point - macroregional",null,null,"WP1,Act.1.2"]
["Meeting","23th TSG 3 Meeting","Q4","tbc","macroregional",null,null,"TSG and PCs","Pillar 3","Facility Point - macroregional",null,null,"WP1,Act.1.2"]
["Meeting","26th TSG 4 Meeting","Q4","tbc","macroregional",null,null,"TSG and PCs","Pillar 4","Facility Point - macroregional",null,null,"WP1,Act.1.2"]
["Meeting","3rd TSG 5 Meeting","Q4","tbc","macroregional",null,null,"TSG and PCs","Pillar 5","Facility Point - macroregional",null,null,"WP1,Act.1.2"]
["Meeting","22nd Meeting of EUSAIR TSG2 on Energy ","Q4","26/11/2025","macroregional","Italy and online","Trieste/ hybrid event","TSG and PCs","Pillar 2 - Energy","Facility Point - macroregional",null,null,"WP1, Act. 1.2","PP6 RAFVG"]
["Event","Workshop on EUSAIR Master Plan on Energy 2026 ","Q4","26/11/2025","macroregional","Italy and online","Trieste/ hybrid event","TSG and PCs, Stakeholders","Pillar 2 - Energy","Facility Point - macroregional","The Workshop will be held during the morning of 26 November 2025, while the afternoon of the same day would be devoted to the 22nd Meeting of the EUSAIR TSG2 on Energy.",null,"WP1, Act. 1.2","PP6 RAFVG"]
["Event","Development of passenger rail connections and interoperability along the routes of the ETC Western-Balkans Eastern Mediterranean (WBEM)","Q4","November","macroregional","Italy","Rome",null,"Pillar 2 - Transport",null,"Interministerial event back to back to the TSG2 Transport: focus on international passenger connections and the new European Transport Corridor (ETC).                                  Target groups involved tbd.",null,"WP1, Act. 1.2","PP6 RAFVG"]
["Activity","Coordination meetings with thematic steering groups and Pillars Coordinators","Q1, Q2, Q3, Q4"," ","regional/local","Other","Tirana","TSG and PCs, Stakeholders, MAs/Funds coordination authorities","Cross Pillar","StEP"," "," ","WP3","P3-SASPAC"]
["Meeting","4th Project Steering Group meeting ","Q4","December","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.3","all"]
["Activity","Progress Report 2024","Q4","December","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP4,Act.4.1","PP5-EYSSAE"]
["Event","AI Shift: Tools, trends & tips for EU macro regional strategies","Q4","09/12/2025","cross-MRS","ONLINE",null,"all","Cross Pillar","INTERACT","Organised by Interact and DSP"]
["Meeting","Meeting of MRS Supporting units","Q3","tbd","cross-MRS",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.4","LP"]
["Meeting","Meeting of Communication network","Q2","tbd","macroregional","ONLINE",null,"EGP","Cross Pillar","Facility Point - macroregional","Meeting between FP PPs and their communication officers",null,"WP2,Act.2.1","LP, all"]
["Activity","Joint EUSAIR Communication Strategy","Q2","March","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.1","LP, all"]
["Activity","EUSAIR website update","Q3","September","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.1","LP"]
["Activity","Study on possible complementarities between S3 shared priorities in EUSAIR region","Q2","March","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP3,Act.3.1","LP"]
["Activity","EGP Guidelines","Q1","March","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.2","LP"]
["Activity","Revision of RoP for GB and TSGs","Q3","October","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.1","LP"]
["Activity","Pillar Roadmap for Actions","Q2","June","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.4","LP"]
["Activity","Analysis of trends - socio-economic state of the region","Q4",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP3,Act.3.1","LP"]
["Activity","Study - support to enlargement process","Q4",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP3,Act.3.1","LP"]
["Activity","Youth actions in 2025","Q2","May, October","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3","LP"]
["Activity","Photography Contest","Q4",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.1","LP"]

{"sheet":"WORKLPAN 2024","index":1,"n_rows":114,"n_cols":17,"rows_kept":114,"cut":false,"hidden":false,"merged":[[6,15,7,20],[3,9,4,9],[3,10,4,10],[3,12,3,13],[3,11,4,11],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,3,4,3],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,4,4,4],[3,5,4,5]]}
[]
["ANNUAL EUSAIR WORKPLAN FOR 2024"]
["Prepared by EGP in cooperation with Pillar Coordinators and Presidency including all EUSAIR  events and main activities/processes regardless of funding source"]
["Type of activity","Title of event\n\nTitle of activity (and phase if relevant)","Term\nDuration\n(quarter of the year)","Date, if relevant","Level - macro-regional, national, regional/local","Location country, if relevant\n\nOnline","Location town, if relevant\n\nHybrid","Target groups\n\nInvolved\n","Pillar related ","Main organiser \n(more details to be provided in column N)","Other important information","Communication coverage needs foreseen","Only for events/activities- supported by EGP"]
[null,null,null,null,null,null,null,null,null,null,null,null,"Application Form\nNo. of Work Package \nNo. of activity","PPs involved"]
["Meeting","Technical meetings of NCs and PCs","Q1","2024-02-21","macroregional","Croatia","Zagreb","National Coordinators, Pillar Coordinators, EGP","Cross Pillar","Facility Point - macroregional",null,"no","WP1,Act.1.1,1.2","LP, all",null,null,"- selection from drop down"]
["Event","Kick of conference of the governance support projects","Q1","2024-02-21","macroregional","Croatia","Zagreb","National Coordinators, Pillar Coordinators, TSG and PCs, EGP, Stakeholders, Media","Cross Pillar","SP4EUSAIR","The Conference shall gather stakeholders from the Adriatic and Ionian Region representing the relevant political and technical levels to enhance the efficient implementation of the EUSAIR ","yes - website, social media","WP1, Activity 1.4","LPs of EGP, all PPs",null,"If you want to see the whole text go to the cell(s) you want to read and click on Wrap Text in the Home menu"]
["Meeting","22nd EUSAIR Governing Board","Q1","2024-02-22","macroregional","Croatia","Zagreb","Governing Board","Cross Pillar","Facility Point - macroregional",null,"no","WP1,Act.1.1","LP, all"]
["Meeting","2nd EGP Joint Steering Committee meeting","Q1","24-25 January 2024","macroregional","Italy","Trieste","EGP","Cross Pillar","StEP",null,null,null,"all LPs"]
["Meeting","3rd EGP Joint Steering Committee meeting","Q1","8.2.2024","macroregional","ONLINE",null,"EGP","Cross Pillar","Facility Point - macroregional",null,null,"WP2,Act.2.3","all LPs"]
["Meeting","4th EGP Joint Steering Committee meeting","Q2","15.4.2024","macroregional","ONLINE",null,"EGP","Cross Pillar","StEP",null,null,null,"all LPs"]
["Meeting","5th EGP Joint Steering Committee meeting","Q2","2024-05-17","macroregional","Croatia","Šibenik","EGP","Cross Pillar","SP4EUSAIR",null,null,null,"all LPs"]
["Meeting","6th EGP Joint Steering Committee meeting","Q3","2024-09-03","macroregional","ONLINE",null,"EGP","Cross Pillar","Facility Point - macroregional",null,null,null,"all LPs"]
["Meeting","1st StEP project Steering Committee Meeting","Q2","15.5.2024","macroregional","Croatia","Šibenik and online",null,"Cross Pillar","StEP",null,null,"WP1, Act. 1.1","StEP PPs and APs"]
["Meeting","19th TSG 2 Energy Sub-Group meeting","Q2","2024-04-23","macroregional","ONLINE",null,"TSG and PCs, EGP","Pillar 2 - Energy","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP6-FVG"]
["Activity","Written Procedure for TSG 3 Annual Report","Q1","February","macroregional",null,null,"TSG and PCs","Pillar 3","Facility Point - macroregional",null,"no","WP4. Act.4.1","PP10-OI"]
["Event","Thematic Pillar 3 Event - Environmental Quality in the scope of the Interreg IPA ADRION Programme (2021-2027)","Q1","3024-03-14","macroregional","Belgium","Brussels","TSG and PCs, Stakeholders, Media, MAs/Funds coordination authorities","Pillar 3","OTHERS (please indicate who in column K)","Hiring speakers from Directorate-General Environment (ENV)","Event advertisement via organiser’s website and newsletters ","WP1, Act.1.2","PP10-OI"]
["Activity","EUSAIR Youth Council call preparation","Q1","February/March","macroregional",null,null,"Task Force","Pillar 5, Cross Pillar","Facility Point - macroregional",null,"no","WP1,Act.1.3","LP, all"]
["Meeting","7th Youth Consultation Task Force meeting","Q1","26.3.2024","macroregional","ONLINE",null,"Task Force","Pillar 5, Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3","LP"]
["Event","Interreg: developing a vision for the future (9th EUSAIR Forum side event)","Q2","14.5.2024","macroregional","Croatia","Šibenik","all","Cross Pillar","OTHERS (please indicate who in column K)","Main organizer is CoR",null,"WP1,Act.1.4"]
["Event","9th EUSAIR Forum","Q2","15-16 May","macroregional","Croatia","Šibenik","all","Cross Pillar","Facility Point - macroregional",null,"yes","WP1,Act.1.4","PP4 MINTS"]
["Event","Workshop – Fostering collaboration for effective development of implementation formats","Q2","16 May","macroregional","Croatia","Šibenik","TSG and PCs","Cross Pillar","SP4EUSAIR","This workshop is intended to present the current analysis of project proposals, to exchange opinions and get the feedback from TSGs on what has been done in the context of project development ","yes","WP1, Act 1.1","LP, PP2 MEI"]
["Meeting","23rd TSG4 meeting","Q2","23.4.2024","macroregional","ONLINE",null,"TSG and PCs, EGP","Pillar 4","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP4 MINTS"]
["Meeting","20th TSG2 Transport Subgroup meeting","Q2","26.4.2024","macroregional","ONLINE",null,"TSG and PCs, EGP","Pillar 2 - Transport","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP6-FVG"]
["Meeting","19th TSG1 meeting","Q2","28.5.2024","macroregional","ONLINE",null,"TSG and PCs, EGP","Pillar 1","Facility Point - macroregional",null,"no","WP1,Act.1.2"," PP5"]
["Activity","Cross-MRS working group on strategic communication","Q1","27.2.2024","macroregional","ONLINE",null,"EGP","Cross Pillar","INTERACT",null,null,"WP2,Act.2.4","LP"]
["Activity","Cross-MRS working group on capacity building","Q1","18.1.2024, 22.4.2024","macroregional","ONLINE",null,"EGP","Cross Pillar","INTERACT",null,null,"WP2,Act.2.4","LP, PP5-EYSSAE"]
["Activity","Cross-MRS working group on embedding ","Q2","11.4.2024","macroregional","ONLINE",null,"EGP","Cross Pillar","INTERACT",null,null,"WP2,Act.2.4","LP"]
["Event","Regional Collaborative Logistics (tbd)","Q2","tbd","macroregional","Italy","Bologna","TSG and PCs, Stakeholders","Pillar 2 - Transport","OTHERS (please indicate who in column K)","The event will be organized in cooperation with the CROSSFREIGHT project (ITL-RER), funded through FESR by the IT-HR INTERREG Programme and expected to start in April 2024.\nThe conference aims to identify the main actors of a new logistics system in the EUSAIR area in order to be ready to the shift to a greener logistics system. It will also identify the main points in which Regions and logistics sector can cooperate to make the entire supply chain green and compliant with the targets set by the European Commission.","yes","WP2","PP6-FVG"]
["Event","In the framework of the Adriatic-Ionian area the development of cycling and the ADRIONCYCLEROUTE: the Friuli Venezia Giulia’s best practices and the States-General of Cycling","Q3","2024-10-10","macroregional","Italy","Udine","TSG and PCs, Stakeholders","Pillar 2 - Transport, Pillar 4","OTHERS (please indicate who in column K)","The event will be organized in the framework of the implementation of the cross-pillar and flagship project ADRIONCYCLETOUR, throughout the ongoing embedding at territorial cooperation level (Interreg projects). The event aims to analyse the state of art of the cycling infrastructures and other actions put in place at regional/national/macro regional and European levels to promote cycling but also as “States general on cycling” as a moment of participation and confrontation consultative and proactive discussion between institutions and stakeholders in the sector, in order to foster a culture of cycling and slow mobility, the reduction of pollution, the promotion of active lifestyles and active health. The conference will be organized by FVG Region in the contest of CYROS Interreg Italy-Croatia project and with the support of the Infrastructure department of the FVG Region directly involved in implementing cycling policies and involving in the debate not only regional, national and cross-border actors, but also European experts on cycle design.","yes","WP2","PP6-FVG"]
["Event","Implementation of EU Biodiversity Strategy for 2030: Common macroregional solutions for nature and fisheries in Adriatic Ionian Region","Q2","23.4.2024","macroregional","Croatia","Zadar","TSG and PCs, Stakeholders, Media, MAs/Funds coordination authorities","Pillar 3","EUSAIR Presidency",null,"yes","WP2","PP10-OI"]
["Event","Thematic Pillar 3 Event - Environmental Quality in the scope of the Interreg IPA ADRION Programme (2021-2027)","Q1","14.3.2024","macroregional","Belgium","Brussels","TSG and PCs, Stakeholders, Media, MAs/Funds coordination authorities","Pillar 3","Facility Point - macroregional","Hiring speakers from Directorate-General Environment (ENV)","Event advertisement via organiser’s website and newsletters ","WP1,Act.1.2","PP10-OI"]
["Event","Conference On Transport Connectivity In The Adriatic-Ionian Region-Corridor Western Balkans – Eastern Mediterranean","Q2","2024-04-25","macroregional","Croatia","Zagreb","Pillar Coordinators","Pillar 2 - Transport","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP4-MINTS, PP6-FVG"]
["Event","Promoting the implementation of macro-regional content in Slovenia\"Capacity Building\" for stakehodlers within the EUSAIR Facility point Project, Interreg IPA Adrion 2021-2027","Q2","7.5.2024","national","Slovenia","Ljubljana","Stakeholders","Cross Pillar","Facility Point  - national",null,"no","WP3,Act.3.2","LP, PP 10-OI"]
["Event","8th Youth Consultation Task Force meeting","Q2","2024-05-29","macroregional","ONLINE",null,"Task Force","Pillar 5, Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.3"]
["Activity","EUSAIR Youth Council call open","Q2","15.4.2024","macroregional",null,null,"Youth","Pillar 5, Cross Pillar","Facility Point - macroregional",null,"YES","WP1,Act.1.3, WP2,Act.2.1","LP, all"]
["Activity","EUSAIR Youth council assessment of applications","Q2","June","macroregional",null,null,"Task Force","Pillar 5, Cross Pillar","Facility Point - macroregional",null,"no","WP1,Act.1.3","LP, all"]
["Meeting","EUSAIR Youth Council set-up","Q3","September","macroregional",null,null,"Youth Council","Pillar 5, Cross Pillar","Facility Point - macroregional",null,"yes","WP1,Act.1.3","LP"]
["Activity","Development of newcomers kit","Q2","June","macroregional",null,null,"National Coordinators, TSG and PCs, EGP","Cross Pillar","Facility Point - macroregional",null,"no","WP3, Act.3.2","PP10-OI, PP7-MEA, LP"]
["Activity","Pillar Annual Progress Reports 2023","Q2","June","macroregional",null,null,"TSG and PCs","Cross Pillar","Facility Point - macroregional","support to PCs","no","WP4, Act.4.1","all"]
["Event","Macroregional and Sea Basin Strategies days in Brussels ","Q2","12-13 June","macroregional","Belgium","Brussels","all","Cross Pillar","EUROPEAN COMMISSION ",null,null,"WP2,Act.2.4","all"]
["Meeting","High level group and Four Trio’s meeting ","Q2","14.6.2024","macroregional","Belgium","Brussels","National Coordinators","Cross Pillar","EUROPEAN COMMISSION ",null,null,"WP2,Act.2.4","all"]
["Meeting","2nd Workshop: “Capacity building to further enhance monitoring and evaluation systems in EU macroregional strategies, with a focus on capturing macro-regional change”","Q2","5-6 June 2024","cross-MRS",null,"Vienna","EGP","Cross Pillar","INTERACT",null,null,"WP2,Act.2.4","LP, PP5-EYSSAE"]
["Event","13th Annual Forum of the EU Strategy for the Danube Region","Q2","20-21 June","macroregional","Other","Vienna","all","Cross Pillar","EUSDR",null,null,"WP2,Act.2.4"]
["Activity","Reporting to EC","Q2",null,"cross-MRS",null,null,"National Coordinators, Pillar Coordinators","Cross Pillar","Facility Point - macroregional","support to NCs, PCs","no","WP4, Act.4.1","all"]
["Activity","Report on existing flagships and developed implementation formats ","Q3",null,"macroregional",null,null,"TSG and PCs","Cross Pillar","SP4EUSAIR","Report will summarize the review of existing documents and methodologies that have been developed in the previous FP and FP Plus projects, as well as interviews with TSGs to collect all relevant information. It will help to enable efficient development of the subsequent implementation formats. It will showcase a summary of the realistic state of the art which would serve as an inception phase for the realization of Project 3. The report will include the findings on which the revised EUSAIR Action planwas based along with the recommendations.","no","WP1, Activity 1.1","LP"]
["Event","First on-line meeting of the MA Network  ","Q3",null,"Macroregional ","ONLINE",null,null,"Cross Pillar","StEP","Presentation of the network and related roadmap for next periods","No","WP4, Activity 4.4. Setting up and animating network of Mas","LP"]
["Event","Second on-line meeting of the MA Network  ","Q3",null,"Macroregional (Italy, BiH and Albania) ","ONLINE",null,null,"Cross Pillar","StEP","Presentation of the Guidance Paper -I part ","No","WP4, Activity 4.4. Setting up and animating network of MAs","LP"]
["Event","ESP on-line networking events ","Q3",null,"Macroregional ","ONLINE",null,null,"Cross-pillar","StEP","Organization and technical assistance of the on-line networking events","Yes, by project 1 and 3 ","WP1, Activity\n 1.2 Updating of ESP Platform","All PPs from EGP and PCs"]
["Activity","Collaborative platform for MA network","Q3",null,"Macroregional ",null,null,null,"Cross-pillars ","StEP","It is a preliminary collaborative tool for the MAs networking ","Yes, by project 1 and 3 ","WP1, Activity Updating of ESP platform ","LP"]
["Meeting","Meeting of national WG for EUSAIR","Q2","May","national","Montenegro","Podgorica","Working group","Cross Pillar","Facility Point  - national",null,"no","WP1,Act.1.1,1.2","PP7-MEA"]
["Meeting","Meeting of national WG for EUSAIR","Q1, Q2","tbd","national","Serbia","tbd","TSG and PCs, National Coordinators, Stakeholders","Cross Pillar","Facility Point  - national","Working group for the implementation of EUSAIR meeting on national level. Preparation for Governing Board meeting. Representatives of line ministries to present their activities on the implementation of EUSAIR.","no","WP1","PP9-MEI"]
["Meeting","20th TSG3 meeting","Q2","8-9 April 2024","macroregional","Croatia","Zagreb","TSG and PCs, EGP","Pillar 3","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP10-OI"]
["Activity","Common Visual Identity development","Q3","September/October","macroregional",null,null,"all",null,"Facility Point - macroregional",null,"yes","WP2,Act.2.1","LP"]
["Activity","Joint EUSAIR Communication Strategy","Q3","September/October","macroregional",null,null,null,null,"Facility Point - macroregional",null,"yes","WP2,Act.2.1","LP, all"]
["Activity","EUSAIR website update","Q3","September/October","macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,"yes","WP2,Act.2.1","LP"]
["Activity","Capacity building needs assessment","Q2, Q3",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,"no","WP3, Act.3.2","PP10-OI, PP7-MEA"]
["Activity","Study on links between AP and accession chapters","Q2, Q3, Q4",null,"macroregional",null,null,null,null,"Facility Point - macroregional",null,null,"WP3, Act.3.1","LP, all"]
["Activity","Supporting the EUSAIR Embedding into IPA III Programmes","Q2, Q3, Q4",null,"macroregional",null,null,null,"Cross Pillar","StEP","The timing of the start of all activities depends on the date of signing of the SC which is precondition for launching of the tender procedure. Additional conditionality is related to DG NEAR’s plans regarding the three available programming.","TBD","WP 5\n\nPreparation and launching of the tender (service), evaluation, contracting, inception period, start of actual activities (1 to 4)","PP 2, LP, Italian NC (MFAIC"]
["Activity","Launching the call for contracting the project coordinator  ","Q2/Q3",null,"national",null,null,null,null,"StEP","Day to day project implementation ","NO","WP3","PP3 - SASPAC"]
["Activity","Launching of a market research to contract an expert in Community and Content Management to support the ESP","Q2/Q3",null,"national",null,null,null,null,"StEP","Day to day project implementation ","NO","WP1, WP2","LP - RM"]
["Activity","Launching of a market research to contract an expert in activities supporting the embedding process","Q2/Q3",null,"national",null,null,null,null,"StEP","Day to day project implementation ","NO","WP4","LP - RM"]
["Event","Workshop on project financing","Q3","tbd",null,"Italy","Rome","TSG and PCs, Stakeholders, MAs/Funds coordination authorities","Pillar 2, Cross Pillar",null,"Tentative event","tbd","WP2","PP6-FVG"]
["Event","Workshop on LNG logistics","Q3","tbd",null,"Italy","Trieste/Ancona","TSG and PCs, Stakeholders","Pillar 2",null,"Tentative event","tbd","WP2","PP6-FVG"]
["Event","Mediterranean Coast and Macroregional Strategies Week","Q3","16-20 September","cross-MRS","Slovenia","Izola","all","Cross Pillar, Pillar 3","Facility Point - macroregional",null,"yes","WP1, Act.1.2","PP10-OI, LP"]
["Meeting","Meeting of EUSAIR S3 Authorities ","Q3","2024-09-17","macroregional","Slovenia","Izola","Pillar Coordinators, TSG and PCs, Stakeholders","Cross Pillar","EGP",null,"no","WP2, Act.2.2","FP-LP, StEP-LP"]
["Meeting","Meeting of MRS supporting units","Q3","2024-09-20","cross-MRS","Slovenia","Izola",null,"Cross Pillar","Facility Point - macroregional",null,"no","WP2,Act.2.4","LP"]
["Activity","Post 2027 Cohesion Policy Consultation","Q3, Q4","July-December 2024","macroregional",null,null,"all","Cross Pillar","Facility Point - macroregional",null,"yes","WP3,Act.3.1","LP, all"]
["Meeting","Meeting of Communication network","Q3","18.10.2024","macroregional","ONLINE",null,"EGP","Cross Pillar","Facility Point - macroregional","Meeting between FP PPs and their communication officers","no","WP2,Act.2.1","LP, all"]
["Activity","MAs network background and methodological paper ","Q3",null,"Macroregional ",null,null,null,"Cross-pillars ","StEP","It is a preliminary collaborative tool for the MAs networking","Yes, by project 1 and 3 ","WP4, Methodological support to the MAs networks","LP - RM"]
["Activity","Launching a micro-tender for a temporary assignment of experts for SHs database and SHs engagement plan update","Q3",null,"national",null,null,null,null,"StEP","Updating and expansion of the ESP ","N/A","WP3, Activity 3.1","PP3 - SASPAC"]
["Activity","Launching a PRAG public procurement tender for a technical assistance company in the organization of WP3 events","Q3, Q4",null,"national",null,null,null,null,"StEP",null,"NO","WP3","PP3 - SASPAC"]
["Activity","Launching of the public procurement tender for a technical assistance company","Q2/Q3",null,"national",null,null,null,null,"StEP","Launching of the public procurement tender for a technical assistance company just after the signature of PA",null,"WP5","PP2 - DEI"]
["Activity","Updating of ESP","Q3",null,"Macroregional ",null,null,null,"Cross Pillar","StEP","Appointed ESP digital management team and and some upgraded tools ","NO","WP1, Activity 1.2 Updating of ESP Platform ","LP - RM"]
["Meeting","Meeting of national WG for EUSAIR","Q3, Q4","tbd","national","Serbia","tbd","TSG and PCs, National Coordinators, Stakeholders","Cross Pillar","Facility Point - macroregional","Working group for the implementation of EUSAIR meeting on national level. Preparation for Governing Board meeting. Representatives of line ministries to present their activities on the implementation of EUSAIR.","no","WP1","PP9-MEI"]
["Activity","EUSAIR Capacity building and e-learning programme","Q3, Q4",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,"no","WP3, Act.3.2","PP10-OI, PP7-MEA"]
["Activity","Monitoring and evaluation  plan","Q3, Q4",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional",null,"no","WP4, Act.4.1,4.2","PP5-EYSSAE"]
["Event","Promoting EUSAIR in Montenegro – WS for stakeholders","Q3","September/October","national","Montenegro","Podgorica","Stakeholders","Cross Pillar","Facility Point  - national","Tentative event","yes - website, social media","WP3,Act.3.2","PP7-MEA"]
["Meeting","Capacity building workshop meetings (6)","Q4","tbd ","macroregional","Croatia","tbd/ possible hybrid","TSG and PCs","Cross Pillar","SP4EUSAIR","The goal of the workshops is to enable conditions for identifying key strategic ideas and sources of financing for future strategic implementation formats. There will be 6 workshops (in person, online or hybrid), one for each TSG to best address the needs of each one.","yes - website, social media","WP1, Activity 1.2","LP nad PP2 MEI"]
["Activity","6 Thematic steering group working reports on key strategic ideas ","Q4",null,"macroregional",null,null,"TSG and PCs","Cross Pillar","SP4EUSAIR","Under the guidance of Project 3, TSG working reports will be produced, one for each TSG. The Reports should highlight specific key strategic ideas in line with flagships and other EU policies. This will ensure the top-down approach.","no","WP1, Activity 1.2","LP nad PP2 MEI"]
["Activity","Knowledge based report on established key strategic ideas ","Q4",null,"macroregional",null,null,"TSG and PCs","Cross Pillar","SP4EUSAIR","This document will present a pool of key strategic ideas attuned to the needs of stakeholders and EUSAIR flagships.  The report, serving as a knowledge base, will ensure evidence based development of future strategic implementation formats. Results of the Activity 1.1. will also be incorporated into the report. The Knowledge based report will be created based on TSG working reports and will represent the sum up of all the findings gathered through the top-down and bottom-up approaches.","no","WP1, Activity 1.2","LP"]
["Event","New ESP Launch on-line Event ","Q4",null,"Macroregional ","ONLINE",null,null,"Cross Pillar","StEP","It is the meeting to present the first new tools of the upgraded ESP","Needed communication coverage support by PP1 and PP3 ","WP 2, Activity 1.2 Updating of ESP Platform ","All PPs from EGP and PCs"]
["Activity","Data knowledge review and sharing from projects relevant to EUSAIR","Q4",null,"Macroregional ",null,null,null,"Cross Pillar","StEP","The 2021.2027 NEW ESP DATABASE will be expanded to include other funding source, such as mainstream programs. ","Yes, by project 1 and 3 ","WP2, Activity 2.2. Data knowledge review and sharing from projects relevant to EUSAIR","LP - RM"]
["Activity","Study on possible complementarities between S3 shared priorities in EUSAIR region","Q4",null,"macroregional",null,null,null,"Cross Pillar","Facility Point - macroregional","The ToR and public procurement will be prepared this year, but the study will be conducted next year.",null,"WP2,Act.2.2","LP"]
["Meeting","3rd Workshop: “Capacity building to further enhance monitoring and evaluation systems in EU macroregional strategies, with a focus on capturing macro-regional change”","Q3","2024-09-26","cross-MRS","ONLINE",null,"EGP","Cross Pillar","INTERACT",null,"no","WP2,Act.2.4","LP, PP5-EYSSAE"]
["Event","“GR-eco Islands” national initiative","Q3","2024-09-30","macroregional","Greece","Corfu","all","Cross Pillar","Facility Point - macroregional",null,"yes","WP1,Act.1.4","PP5-EYSSAE"]
["Event","EUSAIR Hellenic Presidency kick-off event","Q4","2024-10-01","macroregional","Greece","Corfu","all","Cross Pillar","Facility Point - macroregional",null,"yes","WP1,Act.1.4","LP, PP5-EYSSAE"]
["Meeting","Meeting of Coordination Authorities of the mainstream programmes and NIPACs ","Q4","2024-10-01","macroregional","Greece","Corfu","MAs/Funds coordination authorities","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.4","LP, PP5-EYSSAE"]
["Meeting","Conference on the Western Balkans Corridor\n(Pillar 2/ Transport) - TBC","Q4","2024-10-02","cross-MRS","Greece","Corfu","TSG and PCs","Pillar 2 - Transport","EUROPEAN COMMISSION ","Closed Technical Meeting by\nDG MOVE"]
["Meeting","2nd Project Steering Group meeting - kick-off","Q4","2-3 October 2024","macroregional","Greece","Corfu",null,"Cross Pillar","Facility Point - macroregional",null,"yes","WP2,Act.2.3","all"]
["Meeting","23rd EUSAIR Governing Board and back-to-back meetings","Q4","9-10 October 2024","macroregional","Belgium","Brussels","Governing Board","Cross Pillar","Facility Point - macroregional",null,null,"WP1,Act.1.1","LP, all"]
["Event","European Week of Regions and Cities","Q4","7-10 October 2024","cross-MRS","Belgium","Brussels","all","Cross Pillar","EUROPEAN COMMISSION ",null,null,"WP2,Act.2.4","all"]
["Event","Cycling development in the Adriatic-Ionian area and the Adrioncycleroute. States-general of cycling mobility in Friuli Venezia Giulia Region","Q4","2024-10-10","macroregional","Italy","Udine","TSG and PCs, Stakeholders","Pillar 2 - Transport, Pillar 4","OTHERS (please indicate who in column K)","The event will be organized in the framework of the implementation of the cross-pillar and flagship project ADRIONCYCLETOUR, throughout the ongoing embedding at territorial cooperation level (Interreg projects). The event aims to analyse the state of art of the cycling infrastructures and other actions put in place at regional/national/macro regional and European levels to promote cycling but also as “States general on cycling” as a moment of participation and confrontation consultative and proactive discussion between institutions and stakeholders in the sector, in order to foster a culture of cycling and slow mobility, the reduction of pollution, the promotion of active lifestyles and active health. The conference will be organized by FVG Region in the contest of CYROS Interreg Italy-Croatia project and with the support of the Infrastructure department of the FVG Region directly involved in implementing cycling policies and involving in the debate not only regional, national and cross-border actors, but also European experts on cycle design.","yes","WP2","PP6-FVG"]
["Meeting","Cross-MRS working group on embedding ","Q4","2024-10-17","macroregional","ONLINE",null,"Working group","Cross Pillar","INTERACT",null,null,"WP2,Act.2.4","all"]
["Event","EUSBSR Annual Forum 2024","Q4","29-31 October 2024","macroregional","Other","Visby in Sweden",null,"Cross Pillar","OTHERS (please indicate who in column K)","Baltic Macro-regional Strategy","yes","WP2,Act.2.4"]
["Meeting","Launch Event of WP5 Activities ","Q4","25 October 2024","macroregional",null,"Sarajevo","all",null,"StEP",null,null,"WP5, Act. 5.1.","LP StEP, PP2 DEI"]
["Event","Post 2027 Cohesion Policy Consultations, Youth involvement & participation","Q4","November","macroregional","Greece","tbd","all","Cross Pillar","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Event","Conference on INTERREG Programmes consultation","Q4","November","macroregional","Greece","tbd","all","Cross Pillar","EUSAIR Presidency","Back to back with the consultation of cohesion policy",null,"WP1,Act.1.4","PP5-EYSSAE"]
["Event","EUSALP Annual Forum ","Q4","14-15 November 2024","macroregional","Other","Brdo pri Kranju in Slovenia",null,"Cross Pillar","OTHERS (please indicate who in column K)","Alpine Macro-regional Strategy","yes","WP2,Act.2.4"]
["Event","Inaguration event EUSAIR Youth Council","Q4","November","macroregional",null,null,"Youth Council, National Coordinators, Pillar Coordinators, Stakeholders, Public, EGP","Cross Pillar","Facility Point - macroregional",null,"yes","WP1,Act. 1.3","LP"]
["Meeting","EUSAIR Youth Council inaguration meeting and capacity building ","Q4","21.-23.11.2024","macroregional","Croatia","Dubrovnik","Youth Council, EGP","Cross Pillar","Facility Point - macroregional",null,"no","WP3,Act.3.2","LP"]
["Event","Workshop on connecting the Adriatic Ionian Region through Advanced Technology and Training for the Energy Transition in the Port Sector","Q4","28/11/2024","macroregional","Italy","Trieste","TSG and PCs, Stakeholders","Pillar 2","OTHERS (please indicate who in column K)","The event is organized by Central European Initiative (CEI) and FVG Region (PP6)","yes","WP2","PP6-FVG"]
["Meeting","20th TSG2 Energy Subgroup meeting","Q4","29/11/2024","macroregional","Italy","Trieste","TSG and PCs, EGP","Pillar 2 - Energy","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP6-FVG"]
["Meeting","21st TSG2 Transport Subgroup meeting","Q4","29/11/2024","macroregional","Italy","Trieste","TSG and PCs, EGP","Pillar 2 - Transport","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP6-FVG"]
["Meeting","21st TSG3 meeting","Q4","November","macroregional",null,"tbd","TSG and PCs, EGP","Pillar 3","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP10-OI"]
["Meeting","20th TSG1 meeting","Q4","November","macroregional","Montenegro","tbd","TSG and PCs, EGP","Pillar 1","Facility Point - macroregional",null,"no","WP1,Act.1.2"," PP7-MEA"]
["Meeting","24th TSG4 meeting","Q4","7-8 November","macroregional","Albania","tbd","TSG and PCs, EGP","Pillar 4","Facility Point - macroregional",null,"no","WP1,Act.1.2","PP4-MINTS, PP2-SASPAC"]
["Meeting","Autumn Harvesting event - Post 2027 ","Q4","25-26 November 2024","cross-MRS","Belgium","Brussels","EGP","Cross Pillar","INTERACT",null,"no","WP3,Act.3.1","LP"]
["Meeting","4th Workshop: “Capacity building to further enhance monitoring and evaluation systems in EU macroregional strategies, with a focus on capturing macro-regional change”","Q4","3-4 December 2024","cross-MRS","Belgium","Brussels","EGP","Cross Pillar","INTERACT",null,"no","WP2,Act.2.4","LP, PP5-EYSSAE"]
["Meeting","1st TSG5 meeting","Q4","2024-12-05","macroregional","Croatia","Zagreb","TSG and PCs, EGP","Pillar 5","Facility Point - macroregional",null,"no","WP1,Act.1.3","PP4-MINTS"]
["Meeting","Forum on EUSAIR Financial Dialogue: financing resources for strategic projects of the AI region","Q4","5 December 2024","macroregional","Italy","Ancona","all","Cross pillar","StEP",null,null,"WP4, Act. 4.2","LP StEP"]
["Meeting","TSG Pillar 1 (Blue Development) Meeting","Q4","2024-12-09","macroregional","Greece","Athens","TSG and PCs","Pillar 1","EUSAIR Presidency",null,null,"WP1,Act.1.2","PP5-EYSSAE"]
["Event","Conference on Blue Skills, in collaboration with EU’s DG REGIO, DG MARE, DG ENV and DG EMPL","Q4","2024-12-10","cross-MRS","Greece","Athens","all","Pillar 1","EUSAIR Presidency",null,null,"WP1,Act.1.4","PP5-EYSSAE"]
["Event","Empowered territorial cooperation as pathway towards sustainable regional development in AI MR",null,"2024-12-11",null,"North Macedonia","Skopje","all","Cross Pillar","OTHERS (please indicate who in column K)","Ministry of European Affairs"]

{"sheet":"Drop-downs","index":2,"n_rows":35,"n_cols":8,"rows_kept":35,"cut":false,"hidden":true,"merged":[]}
[]
[null,"TYPE OF ACTIVITY",null,null,"LEVEL",null,null,"TARGET GROUPS"]
[null,"Activity",null,null,"macroregional",null,null,"National Coordinators"]
[null,"Event",null,null,"national",null,null,"Pillar Coordinators"]
[null,"Meeting",null,null,"regional/local",null,null,"TSG and PCs"]
[null,null,null,null,"cross-MRS",null,null,"Youth Council"]
[null,null,null,null,null,null,null,"Governing Board"]
[null,"COUNTRIES",null,null,"PILLARS",null,null,"Working group"]
[null,"Albania",null,null,"Pillar 1",null,null,"Task Force"]
[null,"Bosnia and Hercegovina",null,null,"Pillar 2",null,null,"EGP"]
[null,"Croatia",null,null,"Pillar 2 - Transport",null,null,"EC"]
[null,"Greece",null,null,"Pillar 2 - Energy",null,null,"Stakeholders"]
[null,"Italy",null,null,"Pillar 3",null,null,"Media"]
[null,"Montenegro",null,null,"Pillar 4",null,null,"Public"]
[null,"North Macedonia",null,null,"Pillar 5",null,null,"MAs/Funds coordination authorities"]
[null,"San Marino",null,null,"Cross Pillar",null,null,"Youth"]
[null,"Serbia",null,null,null,null,null,"all"]
[null,"Slovenia"]
[null,"Belgium"]
[null,"Other"]
[null,"ONLINE"]
[]
[null,"ORGANISER ",null,null,null,null,null,"Quarter of the year "]
[null,"EGP",null,null,null,null,null,"Q1"]
[null,"Facility Point - macroregional",null,null,null,null,null,"Q2"]
[null,"Facility Point  - national",null,null,null,null,null,"Q3"]
[null,"StEP",null,null,null,null,null,"Q4"]
[null,"SP4EUSAIR"]
[null,"EUSAIR Presidency"]
[null,"EUROPEAN COMMISSION "]
[null,"Adriatic Ionian Initiative"]
[null,"EUSDR"]
[null,"INTERACT"]
[null,"IPA ADRION"]
[null,"OTHERS (please indicate who in column K)"]

{"sheet":"Drop-down","index":3,"n_rows":35,"n_cols":8,"rows_kept":35,"cut":false,"hidden":false,"merged":[]}
[]
[null,"TYPE OF ACTIVITY",null,null,"LEVEL",null,null,"TARGET GROUPS"]
[null,"Activity",null,null,"macroregional",null,null,"National Coordinators"]
[null,"Event",null,null,"national",null,null,"Pillar Coordinators"]
[null,"Meeting",null,null,"regional/local",null,null,"TSG and PCs"]
[null,null,null,null,"cross-MRS",null,null,"Youth Council"]
[null,null,null,null,null,null,null,"Governing Board"]
[null,"COUNTRIES",null,null,"PILLARS",null,null,"Working group"]
[null,"Albania",null,null,"Pillar 1",null,null,"Task Force"]
[null,"Bosnia and Hercegovina",null,null,"Pillar 2",null,null,"EGP"]
[null,"Croatia",null,null,"Pillar 2 - Transport",null,null,"Stakeholders"]
[null,"Greece",null,null,"Pillar 2 - Energy",null,null,"Media"]
[null,"Italy",null,null,"Pillar 3",null,null,"Public"]
[null,"Montenegro",null,null,"Pillar 4",null,null,"MAs/Funds coordination authorities"]
[null,"North Macedonia",null,null,"Pillar 5",null,null,"Youth"]
[null,"San Marino",null,null,"Cross Pillar",null,null,"all"]
[null,"Serbia"]
[null,"Slovenia"]
[null,"Belgium"]
[null,"Other"]
[null,"ONLINE"]
[]
[null,"ORGANISER ",null,null,null,null,null,"Quarter of the year "]
[null,"EGP",null,null,null,null,null,"Q1"]
[null,"Facility Point - macroregional",null,null,null,null,null,"Q2"]
[null,"Facility Point  - national",null,null,null,null,null,"Q3"]
[null,"StEP",null,null,null,null,null,"Q4"]
[null,"Strategic Implementation"]
[null,"EUSAIR Presidency"]
[null,"EUROPEAN COMMISSION "]
[null,"Adriatic Ionian Initiative"]
[null,"EUSDR"]
[null,"INTERACT"]
[null,"IPA ADRION"]
[null,"OTHERS (please indicate who in column K)"]