## Slide 1
WP3: MONITORING AND EVALUATION OF EUSAIR
12th meeting
of the EUSAIR TSG for Pillar 1 - Blue Growth
7/12/2020

## Slide 2: THREE (3) MAIN ACTIVITIES
Activity 1:
Building the Knowledge Base (KB) relevant to Pillar 1 (Blue Growth)
Activity 2:
Establishing the EUSAIR Monitoring and Evaluation Framework
Activity 3:
Capacity building for public authorities / administrations

## Slide 3: Activity 1: Building the knowledge base relevant to Pillar 1 (Blue Growth)
Pillar 1-related study
Task in progress (to be delivered by end of February, 2021)
Identification study of important information gaps, needs and opportunities to facilitate and foster the design and implementation of EUSAIR flagship actions and projects in the Adriatic - Ionian macro-region (Acronym: Ideal EUSAIR)
Inventory of existing resources at Pillar level
Task completed. The Pillar 1 KB comprises three parts:
Relevant studies (83)
Databases (11) + ESPON European and Macro-Regional Territorial Monitoring tool
Statistics
Group A: DataSet A1: Fisheries and Aquaculture, DataSet A2: Science and Technology)
Group B: Socio-economic and other statistics
An executive summary of Pillar 1 KB has been delivered to the TSG1 members in September 2020
State of play

## Slide 4: Activity 2: Establishing the EUSAIR Monitoring and Evaluation Framework (1)
Monitoring and evaluation framework
Identification of actors involved in monitoring and evaluation activities / Set up of the EUSAIR Monitoring & Evaluation System Task completed
Annual Pillar/TSG Monitoring Reports
1st Pillar 1 Annual Monitoring Report 2019  Task completed
2nd Pillar 1 Annual Monitoring Report 2020  Task in progress (revised version was delivered in November 2020; approval is pending)
Pillar 1 SWOT analysis  Task completed
Defining Pillar 1 monitoring indicators (context indicators, output and result indicators, impact indicators)  Task completed
State of play

## Slide 5: Activity 2: Establishing the EUSAIR Monitoring and Evaluation Framework (2)
Annual Synthetic EUSAIR / Action Plan Monitoring Reports
1st EUSAIR Annual Synthetic Monitoring Report 2019  Task completed
2nd EUSAIR Annual Synthetic Monitoring Report 2020  Task in progress (to be delivered in December 2020)
State of play

## Slide 6: Activity 3: Capacity building for public authorities / administrations
Organisation of 2 macro-regional and 8 national capacity building events
1st macro-regional event (November 7th, 2019, Athens, Greece)  Task completed
2nd macro-regional event & national capacity building events  (2021, to be defined)
State of play

## Slide 7
Thank you very much
for your attention!