## Slide 1
Item 2 - Overview of the Action Plan revision process
4th Revision Working Group meeting
online, 11 July 2023

## Slide 2
Preliminary draft prepared for online Public consultation session at Zagreb Croatian Presidency Kick-Off on 20 June
Sent to Pillar Coordinators
27 June meeting with TSG 3
1st Draft included all comments received until 27 June
1st Draft sent to RWG on 30 June
Comments on Preliminary draft received from Pillar 2 Energy subgroup and Social Pillar
Today to discuss any final corrections
Sending to NCs, PCs, TSGs, EC and line DGs on Friday, 14 July?
1st Draft

## Slide 3: Strategic consultation – revision of EC Communication
Agreed at GB on 27 April
Request from MS to be sent to EC  to receive approval before final EC input paper is submitted to EC
EC sent timeline and letter example
Letter to be discussed, agree today, final version by Friday, to be signed by end of July
Who signs the letter?

## Slide 4: EC – Indicative timeline
 | weeks |  | months
MS letter to Council | A |  | A
Council conclusions & request to EC | Y = A + 24 weeks |  | 6
Input paper to EC | B |  | B
Analysis by EC | C = B + 4 weeks |  | 7,5
Discussion with EUSAIR stakeholders | D = C + 2 weeks |  | 
Drafting the new communication and the action plan | E = D + 8 weeks | E > Y | 
First intra and interconsultations within EC | F = E + 3 weeks |  | 
Revised draft Communication + Action Plan modified | G = F + 3 weeks |  | 
Formal EC consultations, including cabinets and senior mgt | H = G + 6 weeks |  | 
Adoption procedure (including translations) | I = H + 4 weeks | I = B + 30weeks | 
 |  | total | 13,5

## Slide 5
Process approved
October 2022
M1
Agreement on the process of the revision
March-May 2023
M2
Strategic and thematic consultation
First
draft of EC input docs
June/July 2023
M3
Drafting
Sep
Oct
Dec
EUSAIR revision timeline
2022/2023
jan
apr
jul
oct
jan
apr
jul
oct
jan
apr
AP pillars, topics/AP structure/ governance agreed
Final EC input docs - AP SWD/COM
October 2023
M4
EC drafts SWD/Com
Public consultation
Public consultation

## Slide 6
1st Draft to be sent to NCs, PCs, TSGs, EC and line DGs on Friday, 14 July?
EC inputs, national consultations, feedbacks – Summer 2023 and first half of September
Letter to EC – end of July
Countries continue sending nominations for Social Pillar
2nd drafts, fine-tuning
Final EC AP/Com input paper (approved at March GB) and sent to EC?
Next steps

## Slide 7: Thank you!