# Annex 6

Cooperation Framework – Ideation phase

This Annex defines the cooperation framework between Pillars’ Thematic Experts and EUSAIR governance support project teams during the ideation phase, i.e. the phase preceding the formal use of the Toolkit for the preparation and selection of Implementation Formats (IFs). The purpose of this framework is to ensure that strategic ideas emerging across the EUSAIR Pillars are:

- systematically collected and documented,

- aligned with macro-regional needs and the EUSAIR Action Plan priorities,

- transparently prioritised within Thematic Steering Groups (TSGs),

- and, where relevant, efficiently supported towards further development into IFs.

The aim is  to clarify roles, responsibilities, and cooperation modalities prior to the use of Toolkit templates.

- Key actors in ideation phase

The ideation phase involves the following key actors:

- Pillars’ Thematic Experts

- Pillar Coordinators (PCs)

- TSGs

- Stakeholders / Idea Owners

- Governance support project teams

Each actor contributes according to their mandate, while respecting the internal procedures and specificities of each Pillar.

- Role of Pillars’ Thematic Experts

The Pillars’ Thematic Experts act on behalf of the TSGs, in close cooperation with the PCs and TSG members, and serves as a central communication/advisory point wihtin the Pillar governance structure.

The Thematic Experts should:

- Continuously collect and consolidate strategic ideas emerging within the Pillar, including ideas originating from TSG members, national and regional authorities, stakeholders from academia, industry, civil society, and other relevant sectors, outcomes of workshops, policy dialogues, and macro-regional events.

- Define the ideation process i.e. strategic idea collection process, in coordination with the PCs and TSG members, thorugh defining:

  - The method of strategic idea collection (e.g. via open calls, public consultations, targeted national consultations, internal TSG discussions),

  - the scope and level of detail required at the ideation stage, i.e. how strategic ideas should be submitted to respective TSGs, taking into account Pillar thematic specificities and internal TSG procedures. This may, but is not limited to, include defining whether idea owner (applicants) are required to provide:

    - a short topic description and rationale,

    - indicative alignment with EUSAIR Action Plan priorities,

    - contact information.

Where relevant, TSGs may refer to the applicable templates and guidance provided in the Annexes to the Manual when defining these requirements.

  - the timeline for idea submission and review.

- Support coordination and prioritisation of ideas within the Pillar, including:

  - facilitating internal discussions within the TSG,

  - supporting the definition of idea prioritisation mechanisms (e.g. consensus-based decision, voting systems among TSG members, decision led by the PC),

  - ensuring transparency and traceability of prioritisation decisions.

- Act as the main contact point between the Pillar (PC and TSG) and the Governance support project teams during the ideation phase, ensuring efficient communication, alignment of expectations, and avoidance of duplication of efforts.

- Role of Governance Support project teams in the ideation phase

Governance support project teams play a supportive and enabling role in the ideation phase, without interfering with the internal decision-making autonomy of the TSGs.

In the ideation phase, Governance support project teams should:

- Provide methodological and procedural support, upon request, to TSGs and Thematic Experts in designing or refining ideation processes (e.g. structuring open calls, consultation formats, or idea collection workflows).

- Support capacity-building activities related to ideation, such as workshops, thematic meetings, or awareness-raising actions aimed at encouraging stakeholders to submit strategic ideas. TSGs and Pillars’ Thematic Experts are invited to propose or request such capacity-building activities based on identified needs, thematic specificities, or gaps observed within the Pillar.

- Offer targeted advisory support once a TSG has identified priority ideas and determined that additional external support is required to advance them further.

Governance support project teams do not take decisions on idea prioritisation or endorsement; these remain under the sole responsibility of the respective TSGs.

- Transition from ideation to further development

Once strategic ideas have been collected and prioritised within a Pillar:

- The TSG, supported by the Thematic Expert, decides whether an idea should:

  - remain at the strategic discussion level,

  - be further elaborated using the Toolkit templates, and/or require targeted external expert support prior to formal IF preparation.

- If further development is envisaged, idea owners may be requested to:

  - complete the relevant profiling template from the Manual (Annexes 1–4, if applicable),

  - and/or submit an External Expert Engagement Form (Annex 5) if expert support is deemed necessary.

- Where external support is required and endorsed by the TSG, Governance support project teams may engage such support in line with their internal rules and procedures, based on:

  - the completed Annex 5,

  - or other agreed arrangements between the Thematic Expert and the Governance support project representative.

Throughout this transition, Thematic Experts should continue cooperating with Governance support project teams to ensure coherence between Pillar priorities and the scope of external assistance.

- Guiding principles

The cooperation framework in the ideation phase is guided by the following principles:

- Pillar autonomy: Each TSG defines its own internal ideation (strategic idea collection) and prioritisation procedures.

- Strategic alignment: All ideas should contribute to macro-regional needs and EUSAIR Action Plan priorities.

- Transparency: Roles, responsibilities, and decision-making processes should be clear, documented and communicated to relevant governance support project teams.

- Flexibility: Procedures may be adapted to thematic and institutional specificities of each Pillar.

- Continuity: The ideation phase provides a structured bridge towards the formal use of the Toolkit and IF development, ensuring timely progression and supporting the operationalisation of the Strategy and EUSAIR Action Plan.